Q1. Sourcing methods to find Federer companies across India

- Startup/Company databases

- Tracxn, Crunchbase, Tofler, ZaubaCorp

- Useful for finding specialty manufacturing companies, funding status, ownership, and sector classification.

- Industry associations

- CII, FICCI, BioAsia, Pharmexcil, CPHI exhibitor lists

- These concentrate technical manufacturers and export-oriented businesses.

- Government/regulatory databases

- DSIR recognized R&D units

- CDSCO medical device approvals

- DPIIT startup database

- PLI beneficiary lists

- Useful for identifying differentiated and growth-oriented firms.

- LinkedIn + Naukri

- Check hiring activity (5+ recent roles), technical leadership, founder profiles.

- Export/import databases

- ImportGenius, ExportersIndia, IndiaMART, DGFT exporter directories

- Good proxy for export-active and expanding manufacturers.

Limitations

- Data can be stale or incomplete.

- Ownership changes require manual validation.

Q2. 1000-company plan (1 month)

Week 1:
Build raw database of ~5000 companies from directories and industry databases.

Week 2:
Use AI + scraping scripts to score companies on:
C1 Manufacturer
C2 India-based
C3 Differentiated
C4 Technical decision-maker
C5 Growing sector
C6 Growth signals

Week 3:
Manual review top ~1500 shortlisted companies to remove false positives.

Week 4:
Finalize 1000 ICP-qualified companies and create outreach-ready CSV.

Expected yield

- Raw list: 5000

- AI shortlisted: 1500

- Final qualified: 1000